## Sheet1
Research Project:
Alzheimer’s disease
|  | Year 1 | [11 empty] | Year 2
| GANTT CHART | 2010 | [8 empty] | 2011 | [11 empty] | 2012
|  | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dis | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dis | Jan | Feb | Mar
1 | Literature Review
2 | Ethics Approval Committee
3 | AS-PCR for Detection of CLU Gene Polymorphism
4 | AS-PCR for Detection of CR1 & PICALM Polymorphism | bar: 2011 Jan to 2011 Feb
5 | Subject Screening | bar: 2011 Jan to 2011 Sept
6 | Processing of Data & Statistical Correlation | bar: 2011 Jul to 2011 Nov
7 | Report and Documentation
|  | Year 1 | [8 empty] | 2011 Apr: Year 2
| MILESTONES | 2010 | [8 empty] | 2011 Jan: 2011 |  | 2012
|  | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dis | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dis | Jan | Feb | Mar
1 | Completion of Literature Review
2 | Completion of Ethics Approval
3 | AC-PCR to Detect Polymorphism Completed | bar: 2011 Feb
4 | Subject Screening Completed | bar: 2011 Sept
5 | Completion of Report and Documentation